## Summary
Summary
Project Description
Project code | 171211HSB - Low Carbon Portfolio
Client | HSBC
Vivid team | JE, TN, SP, JS, SS
Sheet Author
Sheet Auditor
Launch date | 2018-07-23
Workbook Description | Issues log for modelling work on HSBC low carbon portfolio project - when creating issues, tag in a filer, owner, expected completion date and severity to ensure we stay on track.

## Issues Log
Issues Log:
# | Area | Issue | Comments / extra details | Logged date | Resolved date | Creator | Owner | Priority | Area | Creator | Owner | Priority | Key
1 | Model - scenarios | More regional variation - do we need a 'no action in US' scenario? | This will be of interest for HSBC stakeholders and in the public report, but can we do it robustly… No action for now - may do something for November / December | 2018-07-23 |  | SP |  | M | Data - finance | JE | JE | H | Red / H | High priority issues that need to be resolved
2 | Other | Amazon Web Server implementation of the code | This will save time if we have a lot of model runs to do - TN and SP to make a call on cost-benefit | 2018-07-23 |  | SP |  | M | Data - CO2 emissions | TN | TN | M | M / L | Medium and low priority issues that we would like to resolve - include completion date and state when it should be completed if any doubt
3 | Data - finance | Geographic exposure - make sure results make sense… | Ensure values are consistent with Dexter's calculations in the test cases | 2018-07-25 |  | SP | SP | M | Data - oil and gas | SP | SP | L
4 | Data - CO2 emissions | Time series ends in 2016 - financial data is for 2017 | Currently using emissions intensity from 2016 and revenue in 2017 to approximate emissions in 2017, but this has mixed results - emissions intensity of revenue for oil and gas companies fluctuates with revenue for instance (emissions per bbl are consistent but price of bbl fluctuates) Apply trend line approach and calculate delta emissions based on this Use latest available emissions value which is not anomalous (median co2 intensity of revenue screen) | 2018-07-25 | 2018-07-30 | SP | SP | H | Data - green upside | JS | JS
5 | Data - finance | How are we going to clean the product category data? | This will be harder than the geographic exposure analysis for which we already have a very complicated system. See system description below: 1. Make list of 30-40 key sectors which have both high emissions intensity (>100t/MUSD) and high variability in emissions intensity, and decompose these based on activities undertaken within them (product descriptions) 2. Assign new sector definitions on this basis 3. Ethan to go through long list of products and allocate these against key emissions intensive sectors | 2018-07-25 | 2018-08-06 | SP | TN | H | Data - scenarios | SS | SS
6 | Data - finance | How are we defining our sectors? | How do we map each TR sector category to real world activities? No cement sector for instance (Building materials) See above | 2018-07-25 | 2018-08-06 | SP |  | H | Model - carbon costs
7 | Data - finance | Mapping of elasticities, MACs, carbon prices and other parameter data | Someone really needs to check our assumptions here and the values used. This happens after we have the market definitions from Ethan TN to run through with SP | 2018-07-25 | 2018-08-06 | SP |  | H | Model - demand destruction
8 | Model - carbon costs | Cost pass through rates - industry average should not be 1… | Empirical estimates of cost pass through rates in each sector as proposed by Robert R? Set up a meeting with Robert R | 2018-07-25 | 2018-08-06 | SP |  | H | Model - green upside
9 | Data - green upside | FTSE Russell green revenues dataset - how do we map shares to green sectors if we don't receive the breakdowns | Highly likely that Thomson Reuters won't give us the breakdown - upgrade issue priority to High if this is not received by 30/07 | 2018-07-25 | 2018-08-06 | SP |  | H | Model - scenario likelihood
10 | Data - finance | Final dataset from Stephanie | We need this as soon as possible from Stephanie - upgrade issue priority to High if not received by 30/07 | 2018-07-25 | 2018-08-03 | SP | SP | H | Model - scenarios
11 | Other | Model run years - use a subset to save time | Running the model across our scenarios for one parameter set already takes 2 mins - this will rise Can we get around this by running the model at 5 year intervals after 2025? This will be an investment of 2-3 hrs to work out whether model results are materially affected and to check the runs | 2018-07-25 |  | SP |  | M | Other
12 | Model - scenarios | Carbon price path - starts in 2020 | Adam H prices start in 2020, but we interpolate in all periods so 2017 (0$/t) is interpolated with 2020 (40$/t) so it looks like action is immediate How do we want to get around this? Pushing action back to 2020 will result in a sudden jump in the carbon price. Set to be 0 before 2020 (cliff edge start) | 2018-07-25 |  | SP |  | H | Outputs - charts
13 | Model - demand destruction | Coal stranding analysis | Set up Ethan on this task and work out how it will feed into the other analysis, including Justine's if necessary Justine to do this | 2018-07-25 |  | SP |  | H | Outputs - interface
14 | Model - carbon costs | Scope 3 emissions methodology and implementation | Need to research this and implement as necessary - this is not a small analytical task | 2018-07-25 |  | SP |  | H
15 | Model - carbon costs | Scope 2 methodology implementation |  | 2018-07-25 |  | SP |  | H
16 | Data - green upside | Orbis IP data cleaning | Data needs to be merged together, cleaned and checked - a small subset of the IPC codes are part of the green inventory yet Santhosh (BvD) claims that they are all based on green patent (only) analysis so what's the explanation here? If we need additional information from Orbis, get back to them and Stephanie ASAP | 2018-07-25 | 2018-07-30 | SP | SP | H
17 | Model - demand destruction | How do we integrate stranding analysis results into the carbon cost model? | The existing approach is to NPV the stranding impacts, deduct this from BAU market cap (profit flows) and then run the carbon cost model, but clearly this misses key temporal features of the asset stranding analysis. Can we improve on this? | 2018-07-25 |  | SP |  | L
18 | Outputs - charts | Refining the risk-return figure | Ideally, we would like a figure that is easy to read and conveys the two key messages: 1. Risk and return vary considerably by sector and by company 2. There is a large range of climate winners and losers within each sector, and this is often larger than inter-sectoral variation. Different scenarios figure for September | 2018-07-25 |  | SP |  | M
19 | Outputs - interface | Create the interface… | This is very nice to have but is much lower priority than the modelling tasks mentioned above. | 2018-07-25 |  | SP |  | L
20 | Data - finance | Corporation tax values | There's something strange going on in the values here - some of the rates are above 100% (822%) How do we interpret this and do we need to talk to Stephanie / Eric (TR) | 2018-07-25 | 1 | SP |  | H
21 | Model - carbon costs | Power generation model special case | Confirm with Thomas that we no longer need this exception in the model - the power generation sector we have defined from TR contains both conventional utilities and low carbon generators so they are already competing in one market, i.e., there is no need to add in exogenous market contraction induced by the rise of renewables (the MACs already give us this) This is fine | 2018-07-25 | 2018-07-26 | SP | SP | L
22 | Model - carbon costs | New base parameters to be confirmed with TN | What is our process here? What is the neutral choice/ TBC with Robert Ritz on Wednesday | 2018-07-25 |  | SP |  | H
23 | Model - carbon costs | Sensitivity to cost pass through / industry competition structure assumptions | Would be good to have a chat with Robert Ritz about what we believe to be true in terms of the model fundamentals, and how results would change if we alter the underlying assumptions Run lots of sensitivities and give TN the model outputs as: BAU, direct carbon cost impacts, abatement costs, cost pass through decomposed into quantity impact and margin impact, final with 2DS central and base parameters set To start with run the model unconstrained | 2018-07-25 |  | SP | SP | H
24 | Model - scenarios | Set up the R code and spreadsheets to make read in of new scenario data easy |  | 2018-07-25 |  | SP |  | M
25 | Model - carbon costs | Power generation sector results | Absurd results in the power sector - net gain in impacts because profit gains for low margin producers with below average carbon intensity are huge This story is not about quantity reallocation - profit gains occur in our data even when this is set to 0 See above for proposed approach - tick off when resolved | 2018-07-25 |  | SP | SP | H
26 | Model - carbon costs | Low profit margin (Mcap based profit / revenue) + below average carbon intensity = massive gains | How do we get around this issue? The fundamental issues are our estimation of the current profit margin based on profit calculated from the market cap and discount rate, and the assumptions around changes in firm margin in line with the industry price See above for proposed approach - tick off when resolved | 2018-07-25 |  | SP | SP | H
27 | Model - carbon costs | 100% value impairment results coming out | Trace these through to the root cause | 2018-07-25 |  | SP | SP | M
28 | Model - demand destruction | 100% value impairment results coming out | Trace these through to the root cause | 2018-07-25 |  | SP | JS | M
29 | Other | Code structure - set everything up so we can refresh all the code for new data in a systematic fashion Unit tests / test cases of the model with a known solution | This is essential. | 2018-07-25 |  | SP |  | H
30 | Other | Gitlab / Github integration - code needs to be synced to Gitlab | This is essential. Also consider checkpointing of results at COB every day - we need to be able to recreate past results we've shared with clients / put in reports | 2018-07-25 |  | SP |  | H
31 | Model - demand destruction | No results for Kinder Morgan although an E&P company - why? | Part of Rystad dataset so should appear in E&P results. Deleted only gas for this company because their Rystad data produced nonsensical prices (their production reduces at a much faster rate than their Economics). Their oil data is included in the analysis. | 2018-07-25 |  | SP | JS | M
32 | Data - CO2 emissions | Estimation for companies without CO2 emissions data | Replace with sectoral median CO2 intensity rather than mean CO2 intensity (more robust to outliers) | 2018-07-25 |  | SP | SP | H
33 | Data - finance | Separate out E&P component of companies separately - not just based on product shares… | Product category data not of sufficient quality here, so we should do our own research Solved by the product category data - we can never fix revenue share vs. profit share of business | 2018-07-25 |  | SP |  | H
34 | Model - carbon costs | Match parameters in following order: carbon price -> MAC -> elasticity -> market | Makes our lives easier when defining new sectors (do not need to separately define each of these) | 2018-07-25 |  | SP |  | L
35 | Model - carbon costs | Lower bound on number of firms in each market (10?) | Test this with TN and Robert Ritz following cost pass through rate assumptions discussion | 2018-07-25 |  | SP |  | H
36 | Data - scenarios | Change carbon price data to be cliff edge start (2020 first year with non-zero carbon prices) | Our scenarios aren't 2020 start if this is not the case | 2018-07-25 |  | SP | SP | H
37 | Data - oil and gas | Some firms in Rystad data have production data but no Economics data and vice versa | These are not large companies so it shouldn't impact analysis, but if we request data from them again we should make sure they are consistent across sheets If they are small, this is fine - otherwise upgrade status to High | 2018-07-26 |  | JS |  | M
38 | Data - oil and gas | Some firms have negative production or economics data | These are not large companies so it shouldn't impact analysis, but if we request data from them again we should make sure to highlight this to them | 2018-07-26 |  | JS |  | L
39 | Model - demand destruction | Some unit cost/ supply curves have unexpected shapes and price outcomes | There are three firms for which this affects the price spread by producing significant anomalies. Out of these three, only Cabot has a market share higher than 0.0005% and only in Gas- Market share 0.02% (1) Kinder Morgan, (2) Genting Berhad, (3) Cabot Oil and Gas - (1) Gas prices explode in later years because production numbers fall by a much higher factor than economics numbers, (2) - GAS: Negative production data for some years, very high costs data for low production values - produces a price of $1MUSD/cm, LIQUID: strange supply curves because scenarios are the same for some time periods (only differ 2030-2040) with very high costs data, (3) - GAS: higher production in low scenarios than high in later years, LIQUID: low scenario very high price with little production. | 2018-07-26 |  | JS |  | H
40 | Data - oil and gas | Some firms in Rystad data do not have data in some years (e.g. starting only in 2030) | deleted the observations where this is the case in the model | 2018-07-26 |  | JS |  | L
41 | Model - demand destruction | for some VE scenarios we had to extrapolate Rystad data because our scenarios have lower production values than their very low scenario (we never had to extrapolate upward from their high scenario). When doing this by extending the line through the very low and low scenarios resulted in negative extrapolations, decided to draw the line through the origin instead. | Should figure out why our scenarios are lower and whether we need to adjust upward in some fashion | 2018-07-26 |  | JS |  | H
42 | Data - oil and gas | Some firms have the same data across scenarios for several years | these are ignored by the model but might be worth highlighting this to them - once again, not very important companies | 2018-07-26 |  | JS |  | L
43 | Model - demand destruction | The output from the model is somewhat unexpected: we were expecting margin impact to exceed stranding impact in general, but for the majority of companies, the opposite is true |  | 2018-07-26 |  | JS |  | H
44 | Other | Inflation data (price outputs from the model) does not include the increase from carbon prices in oil and gas items and means this item needs to be manually adjusted
45 | Other | Using Price_G from Rystad interpolation plus carbon price per barrell leads to prices below the Rystad BAU projections - this is likely due to our low quantity forecasts and associated low scenario price_Gs | ended up using Price index from model x oil/gas price 2017 + carbon price x carbon content/bbl - this was then above Rystad Central scenario. | 2018-07-26 |  | JS |  | L
46 | Data - finance | ISIN code matching - Shell has a different ISIN code in Trucost to in the financial dataset | Manually matched for now - but we may be missing many other companies because of this | 2018-07-26 |  | SP |  | H
47 | Data - finance | Missing companies in new product categories dataset | SP to investigate (count = 2) and fill in manually (not worth the effort in going back to TR) | 2018-07-26 |  | SP |  | L
48 | Data - finance | 30 markets + green upside, treat all others based on industry level 5 - use simplest possible rule to allocate produce revenues to each sector | This is a bridge over for San Francisco - we will revisit this after September | 2018-07-26 |  | SP |  | H
49 | Model - carbon costs | Other oil and gas sector - how do we deal with the oil and gas sector outside of E&P | Use quantity impacts to work out refinery, and oil and gas service sector impacts for now (assume PC markets) Switch to area under the curve for oil and gas services if we have time | 2018-07-31 |  | SP |  | H
50 | Model - demand destruction | Investigate companies which drop out of fossil fuel demand destruction analysis | Petrochina, SK Innovation, Oil and gas development, PLKNC NAFTOWY ORLEN (Thomson Reuters' names) | 2018-08-10 | 2018-08-16 | SP | JS | M
51 | Model - green upside | Companies with zero aggregate green revenue get binned, but those with at least some green revenue are allowed to grow in industries they don't currently have revenue in from zero market share toward IP share. Those with zero current GR should also be allowed to grow revenue if they have positive IP share. | Has been shelved before, needs to be addressed soon as inconsistent | 2018-09-06 |  | JS | JS | H
52 | Model - green upside | No IP data for some revenue items on company income statements | Use zero IP market share for those who have IP data in other revenue categories. If there is no IP data at all for that company, assume their IP market share = Existing market share | 2018-08-13 |  | JS |  | M
53 | Model - green upside | The only company with only its subsidiary listed in FTSE (Yamaha) has smaller revenue in our data than its subsidiary Yamaha Motor - as well as very different product offering | Deleted for now | 2018-08-16 |  | JS |  | L
54 | Model - green upside | Look at MH suggestion of technology readiness levels | https://en.wikipedia.org/wiki/Technology_readiness_level | 2018-08-16 |  | JS |  | M
55 | Model - green upside | Error when running model code (Green upside model implementation) | future_market_share' is not defined in the scripts - this does not affect the results, as it relates to intermediate chart outputs | 2018-08-29 | 2018-09-06 | SP | JS | L
56 | Model - green upside | Introduced error - NPV impacts are incorrect after SP edits (Sorry Justine) |  | 2018-08-29 |  | SP | SP | H
57 | Model - demand destruction | In the 2DS_delayed scenario, some companies have odd value impairments | See here for details: https://vivideconomics.sharepoint.com/:x:/s/projects/171211HSB/EcdclkxPpQpPvaCMDPiLgHAB6sexxve6JlbTvssPZ-8rqg?e=NGus2T | 2018-09-05 |  | SP | JS | H
58 | Model - demand destruction | Not an issue per se - set up code to export key variables of interest - % profits from gas, % low margin fields, % early production etc. |  | 2018-09-07 |  | SP |  | M
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199